## Slide 1: AbiCountdown Project IDS2018 Exercise – Herbrich, Dennis
Objective
Build a battery-powered, microcontroller-based electronic device in poster size to hang up publicly in school to display a live countdown towards the class of 2001 obtaining their Abitur, with a 1-second resolution, starting from 99 days.

## Slide 2: AbiCountdown Project Front View

## Slide 3: AbiCountdown Project Back View

## Slide 4: AbiCountdown Project Parameters / Limitations / Scope (1/3)
Customer
A second-resolution capable live countdown of the remaining time until reaching the „Abitur“ shall be displayed
The countdown shall be well-visible at a distance of up to 30 meters
The device should be decorative, and shall be attachable to a wall like a picture frame
The device shall not require mains power, and may run off an internal battery supply
Money
No external capital is available, the project must be fully privately financed
Additional cost should not exceed 50 EUR (=effective budget) for the single device
Privately-owned components are used to avoid cost for supplies
Development and production time is zero-cost
The device and its components are reclaimed after the intended one-time use

## Slide 5: AbiCountdown Project Parameters / Limitations / Scope (2/3)
Laws of Nature
Battery capacity must be sufficient to power the device for at least 99 days
The 1 Hz countdown frequency must be sufficiently stable to end the countdown at the expected point in time, without manual adjustments during runtime
A µC firmware must be build, in assembly, for the countdown logic and LED display control
A custom circuit board must be etched, LED daughter boards built, and all components soldered and interconnected properly
The complete device must not weigh more than 5kg
Time
The final product should be built and installed on site when 99 days are left for the countdown => 2 months of time left for development and build from scratch
Installation shall not take longer than 30 minutes on site

## Slide 6: AbiCountdown Project Parameters / Limitations / Scope (3/3)
Capacity
Project team of three students, each with unique strengths in Electrical Engineering, Software Development, and a little bit of both, respectively
Surprisingly well-equipped, private EE lab available
Legal Compliance
The device must be electrically safe, i. E. low-power, low-voltage only
The installed device must be reasonably safe and secure to avoid physical damage and injury

## Slide 7: AbiCountdown Project Biggest Challenges
Frequency Stability
The countdown ran much too slowly, showing an offset of more than an hour per day
The countdown offset was manually corrected on a daily basis, with additional adjustment push-buttons on the back of the device
Battery Life
The LED current draw was much higher than expected, causing the tiny CR2032 to drop out after a few days
The CR2032 was kept as the low-current µC board supply, with an additional pack of AA cells for the LEDs only
µC Firmware Development
Little expertise with ATMEL AVR90S µC assembly, and no available C compiler, made software development tricky and time-consuming
Development took longer than expected, but allowed installation of the final device with 60 days left on the countdown